## Pre Migration
Task | Status
Procure new server with required memory and cpu
Installl and configure posgre database
Application server connectity with new postgre sever
Application software compitibilty with postgre database
Compatibility Analysis check using Microsoft Data Migration Assistant (DMA)
SQL Server Version and Postgre server Compatibility
Database Size and Schema Complexity
Data Type Mapping
Object level modifications check like constraints, indexes, store procedure, functions etc
Security and Authentication
File Paths and Storage
Service Broker/Messaging Systems / other components which are relying on database

## During Migration
Task | Team | Status | Remark
Apply down time on application | Application / Operation Team
Stop other dependent services | Application / Operation Team
Restart MSSQL database | MSSQL
Take object type wise count | MSSQL
Take row count from all user tables | MSSQL
Take object level grants/previlegs | MSSQL
Generate metadata sql DDL scripts | MSSQL
Export table data to csv | MSSQL
Create database, user and schema | Postgre
Import data in tables | Postgre
Create other objects like constarints, index, procedure functions etc | Postgre
Grant required privileges | Posrgre

## Post Migration
Task | Team
Validate objects count | Postgre
Validate table row count | Postgre
check other dependent services (if any) | Postgre
Start other dependent services | Application / Operation Team
Start application | Application / Operation Team

## Rollback plan
Task
If any issue observed during migration activity then stop posrgres database and point application to MSSQL server